## 00 The Request
Request for Institutional Funding — Project RescueSwarm
NIDAR 2026-27, Track 1 · Thapar Institute of Engineering and Technology · Rev A, 2026-08-18 · GENERATED FILE — run hardware/bom/build_university_request.py
WHAT IS BEING REQUESTED
Item | Amount (INR) |  | Note
Total funding requested | 737829 |  | Across four milestone-gated tranches
of which capital — asset retained by the institute | 683306 |  | 92.6% — remains institute property (tab 03)
of which genuinely consumed | 54523 |  | 7.4% — the true unrecoverable cost (tab 04)
WHY THIS IS NOT A 7.38 LAKH EXPENSE
1. Most of it becomes permanent institute property. Three UAV platforms, an RTK base station, a calibrated thrust stand, chargers and field equipment all remain on the department's books after the competition. See tab 03.
2. The institute already contributes 30% of the programme. GPUs, laptops, the 3D printer, the machine shop and lab instruments are already committed, at no new cost. See tab 01.
3. The first decision is 2.90 L, not 7.38 L. Release is gated on demonstrated milestones, and the committee re-decides at each gate. See tab 06.
4. We audited your existing assets before asking. Tab 02 lists 70,500 of equipment that may already be on campus, with the exact question to settle each. Every yes reduces this request and costs the project nothing.
THE PROGRAMME IN ONE VIEW
| INR | Share | Basis
Requested from the institute | 737829 | 66.69% | This workbook
Already provided by the institute | 368500 | 33.31% | Existing assets, tab 01
Total programme value | 1106329 | 100%
Deliberately NOT requested (deferred, tab 07) | 373630 |  | Capability knowingly given up to reduce this request

## 01 Institute Provides
What the institute already provides
Counted at replacement value and REMOVED from the request. Budget rule R1: if the institution owns it, it is not in the ask.
Item | Value if bought (INR) | Where it comes from
GCS laptop | 85000 | Team-supplied
Training compute | 75000 | Institute GPUs — model training needs no new hardware
Backup GCS laptop | 55000 | Team-supplied
Portable power station | 55000 | Institute field power
3D printer | 50000 | Department facility
Equipment cases | 9000 | Institute facility
Soldering station | 9000 | Department facility
Rotary tool + CF extraction | 8500 | Department facility
Bench power supply | 8500 | Department facility
Multimeters | 8000 | Department facility
Fire extinguisher, sand, charging bags | 4000 | Institute facility
Charger PSU | 1500 | Institute facility
TOTAL INSTITUTIONAL CONTRIBUTION | 368500 | 33.3% of total programme value

## 02 Verify Before Buying
Equipment that may already be on campus — please check before sanctioning
If the institute already holds these, they leave the request entirely. This is the only reduction available that costs the project no capability.
Budget line | INR | Likelihood | Who plausibly holds one | The question that actually settles it
Calibrated scale + remaining | 12000 | HIGH | Any lab with a precision balance | Is it calibrated, and can it LEAVE the building on competition day? It decides the Rule C2 weigh-in, so a bench-bound balance does not qualify.
Safety-pilot transmitter | 8000 | HIGH | Aeromodelling / robotics club | Is it ExpressLRS, or can it take an ELRS module? A FlySky or Spektrum set is the wrong protocol and cannot bind to our receivers.
Survey tripod + tribrach | 4000 | HIGH | Civil Engineering survey lab | Standard tribrach with a 5/8 in thread? Available for 8 field days?
Battery chargers | 14000 | MEDIUM | Robotics / aeromodelling club | Does it balance-charge 6S Li-ion at 5 A+, and measure per-cell internal resistance? If it does, the separate cell tester stays deleted.
RTK base receiver | 18000 | CHECK | Civil Engineering DGPS | HIGHEST VALUE, LEAST LIKELY TO JUST WORK. Does it output RTCM3 corrections at 1 Hz to a third-party rover, and is it free during the flight window? A total station is not a substitute.
MAXIMUM REDUCTION IF ALL ARE HELD | 56000 |  |  | Would take the request from 7.38 L to about 6.66 L. Items already confirmed held are NOT listed above -- that reduction is already inside the 7.38 L figure.
Ask the specific question, not the general one. "Do you have a GPS?" gets a yes that turns out to be a total station. Each row above names the property that decides whether the item is actually usable for this project.

## 03 Capital Retained
Capital — durable assets that remain institute property
Conservative test: DURABLE AND DEMONSTRABLY RETAINED. Lines that are partly consumable -- field consumables, and the fabricated ground-truth apparatus -- are counted as consumable in tab 04 even though some of each survives, so this retention claim survives an accounts-office challenge.
Asset | INR | Head | Afterlife once the competition ends
Air vehicles, 3 x 157,800 | 473400 | Air vehicle an | Three flying UAV platforms for student projects, theses and future NIDAR entries.
RTK base receiver | 18000 | Ground segment | Centimetre-accurate GNSS base for any surveying, mapping or robotics work on campus.
Survey tripod + tribrach | 4000 | Ground segment | Returns to general survey use.
Safety-pilot transmitter | 8000 | Ground segment | Reusable across every future UAV built by the department.
Sun hood + observer monitor | 1500 | Ground segment | Field equipment.
Thrust stand | 8000 | Test equipment | Calibrated propulsion test instrument; reusable for every future rotor or propeller study.
Battery chargers | 14000 | Test equipment | General lab charging for all battery-powered student projects.
Calibrated scale + remaining | 12000 | Test equipment | General laboratory instrument.
SUBTOTAL, capital (before duty, GST and contingency) | 538900
With duty, GST and contingency apportioned | 683306 |  | 92.6% of the total request

## 04 Consumables
Consumable — the part that is genuinely spent
This is the true unrecoverable cost of entering the competition.
Item | INR | Why it is consumed
Remaining ground items | 25000 | Cables, mounts, field consumables. RTCM corrections ride the existing telemetry link, so no separate base-to-rover radio is carried.
Fasteners, tape, connectors, filament | 13000 | KEEP.
DGCA registration | 5000 | KEEP. At 6.36 kg these are Small category (2-25 kg) under the Drone Rules 2021 -- only Nano is broadly exempt. UIN registration is required.
SUBTOTAL, consumable | 43000
With duty, GST and contingency apportioned | 54523 | 7.4% of the request — the genuine cost of competing

## 05 Aircraft BOM
Air vehicle bill of materials — 157,800 per aircraft, 3 required
Suppliers are Indian leads at the adopted specification, not held quotations. Lines marked KEEP are held at professional grade deliberately; the rest are hobby-grade where the failure mode is visible and the spec is easy to verify.
# | Component | Specification / part | Grade | Qty | Unit INR | Total INR | Indian supplier lead
1 | Flight controller | Holybro Pixhawk 6C Mini | KEEP | 1 | 22600 | 22600 | Indian distributor (Robu / ElectroPi)
2 | AI accelerator | Edge AI module, >=20 TOPS | KEEP | 1 | 20000 | 20000 | e-con Systems (Chennai)
3 | GNSS RTK primary | AeroNav-series NavIC L1+L5 RTK | KEEP | 1 | 18000 | 18000 | Teravolt Labs (India)
4 | Motors | 5008-class, 340 KV | hobby | 4 | 4500 | 18000 | Reflex Drive (Lucknow) or equivalent
5 | Li-ion cells | 21700 NMC, >=4000 mAh, 40-45 A | KEEP | 18 | 700 | 12600 | GODI India (Hyderabad)
6 | Structure | CF tube, plate and machined clamps | KEEP | 1 | 13000 | 13000 | Kineco Kaman (Goa) + institute machine shop
7 | Camera + lens | Arducam IMX477 + 6 mm S-mount | KEEP | 1 | 11100 | 11100 | Indian distributor
8 | Pack, BMS, PDB, BEC | 6S3P pack, BMS, PDB, BEC | hobby | 1 | 8500 | 8500 | Flameback Tech (Baddi, HP)
9 | RC rx, storage, cooling, mounts | ExpressLRS 2.4 GHz rx (3.5+, native MAVLink) | hobby | 1 | 8500 | 8500 | Zerodrag (India)
10 | ESCs | 60 A, field-oriented | hobby | 4 | 1800 | 7200 | Reflex Drive (Lucknow)
11 | Mesh node + antennas | 5.8 GHz mesh node | hobby | 1 | 6000 | 6000 | FxUAV Technologies (Burla)
12 | Payload system | Servo release, 4 stations | hobby | 1 | 4500 | 4500 | Zerodrag + in-house
13 | Propellers | 18 in carbon | hobby | 4 | 1000 | 4000 | Reflex Drive / UAV Garage
14 | Wiring, connectors | Silicone wire, XT90-S, JST-GH | hobby | 1 | 2400 | 2400 | Polycab / Robu
15 | Prop adapters | 6 mm self-tightening hub | hobby | 4 | 350 | 1400 | Reflex Drive
16 | VEGA co-processor | C-DAC VEGA ARIES v3.0 | KEEP | 1 | 0 | 0 | C-DAC (free to top-100 teams)
| PER AIRCRAFT |  |  |  |  | 157800
| FLEET OF 3 |  |  |  |  | 473400
A fully specified variant of this aircraft was costed at 2,90,546 per unit using named, verified Indian parts throughout (RescueSwarm_BOM_India_Verified.xlsx). The configuration above adopts generic hobby-grade propulsion and ancillaries where the specification is easy to verify on receipt, which is what brings it to 157,800. Motor thrust is unpublished at this grade and is verified on the thrust stand before first flight.

## 06 Release Schedule
Phased release — the committee re-decides at every gate
Funds are not required at once. Each tranche is released only on evidence from the previous one, so the institute's exposure is capped at one tranche.
Tranche | Timing | Phases | INR | Release condition
1 | Months 1-2 | P1-P4 | 290000 | On award. Long-lead components ordered in month one; design point frozen.
2 | Months 3-4 | P5 | 245000 | Released on: ground segment demonstrated, link-loss and low-battery behaviour verified by fault injection.
3 | Months 5-6 | P6-P8 | 175000 | Released on: three airframes weighed, first hover complete.
4 | Months 7-8 | P9-P10 | 114000 | Released on: perception and delivery trials reported with measured figures. Carries the contingency.
| TOTAL |  | 737829 | Cumulative across eight months
These tranches are tied to technical milestones, not to approval thresholds. They are a genuine risk-management structure: if the programme fails to demonstrate a gate, the remaining funds are not released and the institute's loss is capped. They are deliberately NOT a split indent, and should not be presented as one.

## 07 Deferred
What was deliberately not requested
Recorded because a funding request is more credible when it states what it gave up. Each of these is a capability knowingly declined to keep the request small.
Item | Would have cost (INR) | Why it was declined
Spare packs and motors | 74396 | Survives a crash mid-campaign
Sub-GHz safety radio (3) | 58065 | A third independent link; two delicensed bands already carried
Second GNSS receiver (3) | 51000 | Conditional on a P6 magnetometer measurement, not on funding
Training airframe | 37309 | Would fly from week 1 and protect the fleet
Recovery parachutes (3) | 36000 | Permitted, not required. ~40-point bet per crash avoided
Flight insurance | 25000 | MUST BE CONFIRMED against the rulebook and DGCA rules before any flight
Spare airframe structure set | 25000 | Deferred 2026-08-18. Was the crash cover; one hard landing now ends the campaign
Spare propellers and stock | 21400 | Deferred 2026-08-18. Propellers are the most consumed item in flight test
Spare compute module | 20000 | Removes a single point of failure
Field data campaign | 15000 | Detection recall measured rather than modelled
Relief kits (14) | 5600 | Deferred 2026-08-18. THE DELIVERED PAYLOAD. Rule C6 fixes it at 200 g; without kits there is nothing to release and the delivery task scores nothing
Ground-truth apparatus | 4860 | Deferred 2026-08-18. Detection recall now has no target to be measured against
TOTAL DEFERRED | 373630 | Capability given up to reduce this request.
ONE ITEM NEEDS A DECISION FROM THE INSTITUTE, NOT FROM US: third-party insurance was deferred at the team's direction, but cover is commonly mandatory for unmanned operations in India. It must be confirmed against the DGCA rules and the competition rulebook BEFORE ANY FLIGHT. If it is required it ceases to be a budget choice, and 25,000 returns to the request.

## 08 Method
How these figures were produced
So that any number here can be traced, challenged and reproduced.
Single source of truth | Every figure is imported from docs/proposal/figures/competition_budget.py. Nothing in this workbook is typed by hand, so it cannot drift from the technical proposal.
Customs duty | 22%, applied only to the imported share of ex-GST quoted lines. Indigenous content is 35.5%, computed per line, not estimated.
GST | 18%, applied only to lines quoted ex-GST. Indian retail prices already include GST and are NOT taxed again — an earlier revision did this and overstated the request by 1.64 L.
Contingency | 15% on the whole, carried in the final tranche.
Rule R1 | If the institution already owns it, it is not in the request. This removed 368,500 (tab 01). Tab 02 lists what still needs checking.
Rule R2 | If it can be built rather than bought, it is costed as built — the thrust stand, ground-truth apparatus and sun hood are fabricated.
Rule R3 | Spares cover what CRASHES, not what fails rarely and costs a fortune. Accepted risks are stated in tab 07, not hidden.
Rule R4 | Hobby grade where the failure mode is visible and the specification is easy to verify; professional grade where it is not.
Known open item | The generic motors publish no thrust curve. Thrust-to-weight is therefore a requirement rather than a measurement until the thrust stand runs in phase P5. This is stated rather than assumed away.
Reference documents | hardware/bom/RescueSwarm_BOM_India_Verified.xlsx holds the fully specified variant with named parts and verified links. docs/proposal/ holds the technical proposal with the engineering justification.